## Sheet1
|  |  |  | Week #1 (18 hrs / week) - 2 Weeks - Sprint 1 |  |  | Week #2 (10 hrs / week) | [6 empty] | Week #3 (10 hrs / week) | [6 empty] | Week #4 (10 hrs / week)
Backlog Item | Task |  | Initial Estimate (Total Sprint Hours = 40 x 6) | D1 | D2 | D3 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28
|  |  |  | 2021-10-14 | 2021-10-23 | 2021-10-24 | 2014-09-20 | 2014-09-21 | 2014-09-22 | 2014-09-23 | 2014-09-24 | 2014-09-25 | 2014-09-26 | 2014-09-27 | 2014-09-28 | 2014-09-29 | 2014-09-30 | 2014-10-01 | 2014-10-02 | 2014-10-03 | 2014-10-04 | 2014-10-05 | 2014-10-06 | 2014-10-07 | 2014-10-08 | 2014-10-09 | 2014-10-10
|  | Task Owner |  |  | -9 | -18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | Ideal Burndown
|  |  | 72 | Week #1 (18 hrs / week) - 2 Weeks - Sprint 1 D1: #REF!; Week #1 (18 hrs / week) - 2 Weeks - Sprint 1 D2: #REF!; Week #1 (18 hrs / week) - 2 Weeks - Sprint 1 D3: #REF!; Week #2 (10 hrs / week) D8: #REF!; Week #2 (10 hrs / week) D9: #REF!; Week #2 (10 hrs / week) D10: #REF!; Week #2 (10 hrs / week) D11: #REF! | Remaining Hrs (Total)
Requirements Gathering | Analyse API's required | Payal, Madhuri, Shantanu,Sindhana | 26 | Week #1 (18 hrs / week) - 2 Weeks - Sprint 1 D1: 8; Week #1 (18 hrs / week) - 2 Weeks - Sprint 1 D2: 8; Week #1 (18 hrs / week) - 2 Weeks - Sprint 1 D3: 10
| Tech Stack Finalization | Payal, Madhuri, Shantanu,Sindhana | 26 | Week #1 (18 hrs / week) - 2 Weeks - Sprint 1 D1: 8; Week #1 (18 hrs / week) - 2 Weeks - Sprint 1 D2: 8; Week #1 (18 hrs / week) - 2 Weeks - Sprint 1 D3: 10
UML Deployment Diagram | Draw Deployment Diagram according to flow | Payal, Shantanu | 10 | Week #1 (18 hrs / week) - 2 Weeks - Sprint 1 D1: 2; Week #1 (18 hrs / week) - 2 Weeks - Sprint 1 D2: 4; Week #1 (18 hrs / week) - 2 Weeks - Sprint 1 D3: 4
UML Class Diagram | Draw Class Diagram according to schema | Sindhana, Madhuri | 10 | Week #1 (18 hrs / week) - 2 Weeks - Sprint 1 D1: 2; Week #1 (18 hrs / week) - 2 Weeks - Sprint 1 D2: 4; Week #1 (18 hrs / week) - 2 Weeks - Sprint 1 D3: 4
Team:
| Payal | 18 hours / Week
| Shantanu | 18 hours / Week
| Madhuri | 18 hours / Week
| Sindhana | 18 hours / Week
| Total Available Hours During Sprint: | 72