## Sheet1
|  |  |  | Week #1 (18 hrs / week) - 2 Weeks - Sprint 1 |  |  | Week #2 (18 hrs / week) - 2 Weeks - Sprint 2 |  |  |  | Week #3 (10 hrs / week) | [6 empty] | Week #4 (10 hrs / week)
Backlog Item | Task |  | Initial Estimate (Total Sprint Hours = 40 x 6) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28
|  |  |  | 2021-10-14 | 2021-10-23 | 2021-10-24 | 2021-10-26 | 2021-10-27 | 2021-10-28 | 2021-10-29 | 2014-09-27 | 2014-09-28 | 2014-09-29 | 2014-09-30 | 2014-10-01 | 2014-10-02 | 2014-10-03 | 2014-10-04 | 2014-10-05 | 2014-10-06 | 2014-10-07 | 2014-10-08 | 2014-10-09 | 2014-10-10
|  | Task Owner |  |  | -9 | -18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | Ideal Burndown
|  |  | 72 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [14 empty] | Remaining Hrs (Total)
Database preliminary Schema | Come up with DB Schema according to API | Payal, Madhuri, Shantanu,Sindhana | 52 | 8 | 8 | 10 | 13 | 13 | 13 | 13
|  |  |  | 8 | 8 | 10
Project Structure | Finalize Project Structure to start Implementation | Payal, Madhuri | 10 | 2 | 4 | 4 | 2 | 2 | 2 | 4
Logical Decision for API | Analyse logical decisions for every API | Sindhana, Shantanu | 10 | 2 | 4 | 4 | 2 | 2 | 2 | 4
Team:
| Payal | 18 hours / Week
| Shantanu | 18 hours / Week
| Madhuri | 18 hours / Week
| Sindhana | 18 hours / Week
| Total Available Hours During Sprint: | 72