## Sprint
|  |  |  | Sprint #1 (18 hrs / week) |  |  | Sprint2 #2 (18 hrs / week) |  |  |  | Sprint #3 (18 hrs / week) | [6 empty] | Sprint #4 (18 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 18 x 4) | D1 | D2 | D4 | D4 | D6 | D7 | D8 | D9 | D10 | D1 | D12 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28
|  |  |  | 2021-10-14 | 2021-10-23 | 2021-10-24 | 2021-10-26 | 2021-10-27 | 2021-10-28 | 2021-10-29 | 2021-11-07 | 2021-11-08 | 2021-11-13 | 2021-11-16 | 2021-11-18 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-23 | 2021-11-24 | 2021-11-25 | 2021-11-26 | 2021-11-27 | 2021-11-28
|  |  |  | 72 | 70 | 68 | 60 | 52 | 46 | 42 | 58 | 66 | 64 | 62 | 58 | 54 | 51 | 49 | 47 | 43 | 41 | 39 | 35 | 0 | Ideal Burndown
|  |  | 72 | 72 | 51 | 63 | 28 | 25 | 21 | 24 | 56 | 65 | 62 | 62 | 54 | 54 | 52 | [7 empty] | Remaining Hrs (Total)
Enable all users to sign up and login | Design Business Logic | All | 5 | 5 | 10 | 15 | 13 | 13 | 13 | 13 | 6 | 5 | 5 | 5 | 5 | 5 | 5
| Design User Interface | All | 5 | 5 | 10 | 13 | 2 | 2 | 2 | 4 | 9 | 5 | 5 | 5 | 5 | 5 | 5
| Implement Back-End Code | Madhuri,Sindhana | 10 | 10 | 5 | 5 | 2 | 2 | 2 | 4 | 10 | 10 | 11 | 11 | 10 | 10 | 10
| Implement Front-End Code | Shantanu, Payal | 10 | 10 | 5 | 5 | 0 | 0 | 0 | 0 | 10 | 13 | 11 | 11 | 10 | 10 | 10
| Complete Unit Testing | Sindhana, Madhuri | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 13 | 11 | 11 | 11 | 11 | 11
| Complete Regression Testing | Shantanu, Payal | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Write Documentation | All | 10 | 10 | 1 | 5 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 0
Design and start implementation on search and book flights | Decide Business Logic | All | 2 | 2 | 20 | 20 | 3 | 2 | 1 | 2 | 2 | 5 | 5 | 5 | 5 | 5 | 5
| Implement Front-End API | Shantanu, Payal | 5 | 5 | 0 | 0 | 3 | 2 | 1 | 0 | 3 | 5 | 5 | 5 | 2 | 2 | 2
| Implement Back-End APIs | Sindhana, Madhuri | 5 | 5 | 0 | 0 | 3 | 2 | 1 | 0 | 2 | 5 | 5 | 5 | 2 | 2 | 2
Team:
Shantanu | 18 hours / Week
Payal | 18 hours / Week
Madhuri | 18 hours / Week
Sindhana | 18 hours / Week
Total Available Hours During Sprint: | 240